## Sheet2
Summary of Virginia's NewSTEPS Implementation Expenses |  |  |  | Hours |  | Dollars
Phase | Activity | Hours Estimate | Dollar Estimate | Year 1 | Year 2/3 | Avg Rate | Total Hours by Phase | Total $ by Phase
Project | Complete forms to initiate an IT project in Virginia | 120 | 6720 | 60 | 60 | 56
Administration | Create presentation and host multiple webinars to introduce NewSTEPs messaging project to the Virginia Healthcare and Hospital Association | 80 | 4480 | 80 | 0 | 56
| Conduct Kick-off meeting with potential hospital partners, OZ(*) Systems and JMC Consulting | 100 | 5600 | 100 | 0 | 56
| Participate in VA NewSTEPs calls with hospital partners, OZ Systems and JMC Consulting | 64 | 3584 | 44 | 20 | 56
| Prepare and distribute meeting minutes | 44 | 1100 | 24 | 20 | 25
| Prepare project status reports on pilot hospital progress | 44 | 1100 | 24 | 20 | 25
| Participate in monthly calls with NewSTEPs coach | 140 | 7840 | 70 | 70 | 56
| Participate in monthly calls with NewSTEPs all-state participants | 14 | 784 | 8 | 6 | 56
| Project Administration (monthly billing and year-end close out) | 70 | 3920 | 40 | 30 | 56 | 676 | 35128
| Free NBS collection kits offered as incentives for actively participating hospital partners (3 kits/site annually at $780/kit) | 72 | 56160 | 36 | 36 | 780
Procurement | Prepare Sole Source Procurement for HIE Services | 165 | 9240 | 165 | 0 | 56
| Issue PO's for IT contract resources for LIMS and messaging development | 4 | 224 | 2 | 2 | 56
| Issue PO to JMC Consulting Services for informatics support | 4 | 224 | 2 | 2 | 56
| Create MOA with the Health Department to leverage Virginia's Public Health Reporting Pathway for NBS exchanges | 80 | 4480 | 0 | 80 | 56
| Redesign and order new NBS Dried bloodspot cards based on input from Virginia's NBS program staff | 100 | 5600 | 100 | 0 | 56 | 353 | 19768
Onboarding Guide Development | Create NBS Data Exchange Participant Enrollment Form | 15 | 840 | 0 | 15 | 56
| Create data exchange agremeent between OZ/Hospital participants and HIE | 80 | 4480 | 0 | 80 | 56
| Develop a How-To guide for enrolling in VA's NBS Data Exchange Program | 120 | 6720 | 0 | 120 | 56
| Post Onboarding guide and related materials to DCLS Website | 20 | 1120 | 0 | 20 | 56 | 235 | 13160
HIE Development | Create and obtain sign-off on Statework of Work with HIE | 160 | 8960 | 0 | 160 | 56
| Work with HIE and MEDfx development team to make modifications for NBS data exchange | 120 | 6720 | 0 | 120 | 56
| Obtain sign-off from HIE on Onboarding packet | 30 | 1680 | 0 | 30 | 56
| Participate in weekly technical touchpoint calls between IT staff, HIE, OZ and Virginia Department of Health | 20 | 1120 | 0 | 20 | 56
| Prepare and distribute weekly meeting minutes and decision register | 20 | 1120 | 0 | 20 | 56
| Onboard OZ Systems Pilot hospitals to HIE | 10 | 560 | 0 | 10 | 56
| Onboard Non-OZ Systems Pilot hospitals to HIE | 15 | 840 | 0 | 15 | 56
| Test "Hello World" connectivity | 5 | 280 | 0 | 5 | 56
| Test connectivity using certificates issued for partner authentication and payload encryption | 20 | 1120 | 0 | 20 | 56 | 400 | 22400
| Test error and exception handling processes between LIMS, HIE, OZ systems | 20 | 1120 | 0 | 20 | 56
Lims Development | Perform GAP analysis between LIMS and HL7 message guide for lab orders | 160 | 8960 | 40 | 120 | 56
| Conduct requirements gathering sessions with lab staff and review changes to operational processes | 100 | 5600 | 0 | 100 | 56
| Modify LIMS to support NBS e-order processing | 180 | 10080 | 0 | 180 | 56 | 440 | 24640
| Perform GAP analysis between LIMS and HL7 Message guide for lab results | 160 | 8960 | 0 | 120 | 56
| Conduct requirements gathering sessions with lab staff and review changes to operational processes | 80 | 4480 | 0 | 80 | 56
| Modify LIMS to support NBS e-results processing** | 180 | 10080 | 0 | 180 | 56
Message Development | Participate in HL7 NBS HL7 Workgroup | 92 | 5152 | 36 | 56 | 56
| Work with HL7 terminiologist to identify appropriate vocabularies and codes sets | 180 | 14760 | 40 | 140 | 82
| Train IT staff on HL7 message structure and development | 40 | 3280 | 0 | 40 | 82
| Train IT and Lab informatics staff on terminologies and coded vocabularies | 40 | 3280 | 0 | 40 | 82
| Develop process for message structural and content validation | 778 | 71576 | 0 | 778 | 92
| Develop process to parse and load e-orders into the LIMS | 324 | 29808 | 0 | 324 | 92
| Develop process for error and exception handling | 220 | 20240 | 0 | 220 | 92 | 1674 | 148096
| Develop process to extract e-results from the LIMS and translate/map data to HL7 message ** | 324 | 29808 | 0 | 324 | 92
Vendor Systems | Work with OZ staff to perform GAP analysis between NANI system, LIMS and HL7 guide | 220 | 18040 | 40 | 180 | 82
Development | Develop and synchronize data validation rules for NANI and Telepathy and LIMS data entry screens | 120 | 6720 | 0 | 120 | 56
| Review, clean and develop Virginia submitter table for Telepathy | 240 | 6000 | 80 | 160 | 25
| Work with OZ Systems to develop electronic/barcoded label for sample submission | 80 | 4480 | 0 | 80 | 56
| Participate in weekly calls with IT and lab staff, OZ and Pilot Hospital | 110 | 6160 | 0 | 110 | 56
| Participate in OZ Systems Training of Pilot Hospitals | 5 | 280 | 0 | 5 | 56 | 775 | 41680
Direct System Development | Work with hospital staff to perform GAP analysis between hospital system, LIMS and HL7 guide | 160 | 8960 | 40 | 120 | 56
Development | Develop and synchronize data validation rules for Hospital System and LIMS data entry screens | 120 | 6720 | 0 | 120 | 56
| Work with Hospital System to develop electronic/barcoded label for sample submission | 80 | 4480 | 0 | 80 | 56
| Participate in periodic calls with IT and lab staff and Pilot Hospital | 110 | 6160 | 0 | 110 | 56
Testing and | Work with lab, OZ Systems and hospitals to develop use cases | 120 | 9840 | 120 | 0 | 82
Validation | Work with lab, OZ Systems and hospitals to develop test cases and examples of HL7 lab order messages | 120 | 9840 | 120 | 0 | 82 | 400 | 28640
| Work with lab, OZ Systems and hospitals to develop test cases and examples of HL7 lab results messages ** | 120 | 9840 | 0 | 120 | 82
| Post link to required test case on DCLS website | 5 | 280 | 0 | 5 | 56
| Distribute Test cases to OZ Systems and non-OZ Pilot hospitals for use in training and testing | 5 | 410 | 0 | 5 | 82
| Execute Test cases to perform internal QA testing of processes | 120 | 9840 | 0 | 120 | 82 | 130 | 10530
| Distribute Test cases to lab staff for use in training and testing | 5 | 410 | 0 | 5 | 82
| Train lab staff | 30 | 900 | 0 | 30 | 30
| Remediate issues and perform regression testing | 40 | 2240 | 0 | 40 | 56
| Perform parallel testing and obtain production sign-off from Lab | 20 | 600 | 0 | 20 | 30
| Obtain production sign-off from OZ, HIE, Pilot Hospital and Lab | 5 | 280 | 0 | 5 | 56
Implementation ** | Conduct Post Implementation Review and document issues and efficiencies of e-orders and e-results | 45 | 3690 | 0 | 45 | 82
| Review lessons learned and operationalize onboarding process with OZ and non-OZ hospital partners statewide | 50 | 4100 | 0 | 50 | 82
| Ongoing resources required to troubleshoot issues as reported | will have staff dedicated to resolve issues as needed
| * Third Party Vendor - OZ systems ** Hours estimated - Activity still in progress | [5 empty] | 5083 | 344042